Project Title: Educational for Drone (eDrone)

Deliverable Title: Coordination of quality control

| Deliverable Type | Methodology |
| --- | --- |
| Result Number |  |
| Date of Delivery | 1/09/2019 |
| Author(s) | Eulalia Balestrieri (UNISANN) |
| Reviewer | Francesco Lamonaca (UNISANN) |
| Review date | 10/09/2019 |
| Reviewer |  |
| Review date |  |

# Table of Contents

Table of Contents	2

Versioning and Contribution History	3

1. Coordination of Quality Control Approach	4

4. Deadlines	8

5. Example of Template to provide deliverable information	11

6. Example of Template to provide information about Deliverable Versioning and Contribution History	12

# Versioning and Contribution History

The following is the document control for revisions to this document.

| Version | Date | Reason | Modified by |
| --- | --- | --- | --- |
| 01 | 1/09/2019 | Submission of the report to WP5 leader | Eulalia Balestrieri |
| 02 | 14/09/2019 | Modifications of the report after reviews | Eulalia Balestrieri |

Please include here also information on: when was the concept note submitted, when was feedback received, etc.

# 1. Coordination of Quality Control Approach

The purpose for managing quality is to control all the activities related to the validation of the project deliverables assuring a high level of quality. The control of quality is not limited to assure the quality of the project deliverables, but also the quality of the processes used to manage and create the them.

The coordination of quality control activities is strictly related to what established in the in the quality management plan and are focused on the following processes:

| Objects of quality review | Quality Measure | Quality Evaluation Methods |
| --- | --- | --- |
| Project Deliverables | Deliverable Quality Standards Completeness and Correctness Criteria Timeline | Respect of the time line Peer Review Process |
| Organization of meeting, workshop, conferences | Suitability of the goals Suitability of the goal time line Quality of the agenda Quality of the selected speakers Quality of the provided materials Overall quality of the event execution | Respect of the time line Questionnaire |
| Didactics | Suitability of the goals Suitability of the goal time line Quality of the time table Quality of the selected speakers Quality of the provided materials Improvement of the knowledge of the attendances | Respect of the time line Questionnaire |
| ICT platform | Suitability of the platform Easy to use Availability of the platform | Respect of the time line Questionnaire |

# 2. Coordination of Quality Control Objectives

The following are the coordination of quality control objectives of the project reflecting the overall intentions to be applied with regard to quality control throughout the project.

- Coordination of monitoring and controlling partner’s activities.

- Coordination of controlling the quality of deliverables.

- Monitoring the project developments, according to what established in the Quality Plan taking into account deadlines and tasks distribution.

# 3. Coordination of Quality Control Procedure

The initial Quality Control review is the responsibility of each WP Leader who prepares deliverables. The second Quality Control review is the responsibility of WP5 Leader or other Project Partners who confirms that the deliverables represent the Project Development scope and that the final findings and conclusions meet the Project requirements.

It must be ensured accuracy, completeness, clear and concise readability.

WP5 Leader will control that timely reviews and comments on how to prevent and/or correct errors in the documents prior to their finalization must be provided.

Items to review for quality include but are not limited to clarity of the report, technical adequacy, appropriate level of analysis, completeness and accuracy of the information presented, and regulatory sufficiency. During the reviews, the documents and reports will be also checked for spelling, grammar, and format for compliance with quality control standards.

The Quality Assurance review will be performed by WP5 Leader, to verify the deliverables and carried out activities meet the Quality Plan procedures and Project scope. Any comments from the Quality Assurance reviews will be addressed by the respective project partners.

The Versioning and Contribution History must be included in the deliverables, information about the deliverable type, document author, reviewer, date of delivery and review date must be provided.

Coordination of Quality Control will be carried out according to what established in the Quality Plan in terms of Milestones, Deadlines, Quality Team Roles & Responsibilities, Quality Tools.

# 4. Deadlines

In the following the deadline for each deliverable are reported, with the WP Leader that will coordinate the first quality control activities:

| d1.1 | State of the art report on last generation technologies for drones and sensors supporting remote control | MUT | Bartosz | Brzozowski | 14/01/2017 |
| --- | --- | --- | --- | --- | --- |
| d1.2 | Workshops on Technology of Drones | MUT | Bartosz | Brzozowski | 14/01/2017 |
| d1.3 | Visits to enterprises | MUT | Bartosz | Brzozowski | 14/04/2017 |
| d1.4 | User needs document | MUT | Bartosz | Brzozowski | 14/07/2017 |
| d2.1 | State of Art of drones laws in Programme Countries | CAA | Constantin | Vozian | 14/03/2017 |
| d2.2 | State of Art of drone laws in Partner Countries | CAA | Constantin | Vozian | 14/03/2017 |
| d2.3 | Workshop on Law and User needs | CAA | Constantin | Vozian | 14/03/2017 |
| d2.4 | Regulatory needs report | CAA | Constantin | Vozian | 14/07/2017 |
| d3.1 | Course program structure and content design | UNIEVRY | Yasmina | Bestaoui | 14/12/2017 |
| d3.2 | ECTS recognition of the course | UNIEVRY | Yasmina | Bestaoui | 14/02/2018 |
| d3.3 | Educational material for the course program | UNIEVRY | Yasmina | Bestaoui | 14/09/2018 |
| d3.4 | Lecturer selection of CTT | UNIEVRY | Yasmina | Bestaoui | 14/09/2017 |
| d3.5 | Enrollment process for CTT course | UNIEVRY | Yasmina | Bestaoui | 14/04/2018 |
| d3.6 | Enrollment process for CIA | UNIEVRY | Yasmina | Bestaoui | 14/05/2019 |
| d3.7 | CTT Deployment | UNIEVRY | Yasmina | Bestaoui | 14/04/2018 |
| d3.8 | CIA Deployment | UNIEVRY | Yasmina | Bestaoui | 14/05/2019 |
| d4.1 | Equipment purchase | MSU | Florentin | Paladi | 14/06/2018 |
| d4.2 | ICT platform setup | MSU | Florentin | Paladi | 14/06/2018 |
| d4.3 | Web content development | MSU | Florentin | Paladi | 14/06/2018 |
| d4.4 | E-learning material for course program | MSU | Florentin | Paladi | 14/06/2018 |
| d5.1 | Design of the quality management system | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d5.2 | Coordination of quality control | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d5.3 | Quality monitoring | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d5.4 | Project documentation | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d5.5 | Final evaluation of the course | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d5.6 | External audit | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d6.1 | Dissemination plan | NPUA | Hrachya | Karapetyan | 14/07/2017 |
| d6.2 | Universities meetings | NPUA | Hrachya | Karapetyan | 14/05/2018 |
| d6.3 | Dissemination workshops | NPUA | Hrachya | Karapetyan | 14/09/2019 |
| d6.4 | Electronic publishing of news and reports | NPUA | Hrachya | Karapetyan | 14/09/2019 |
| d6.5 | Participation to workshops and visits | NPUA | Hrachya | Karapetyan | 14/09/2018 |
| d6.6 | Promotional material | NPUA | Hrachya | Karapetyan | 14/07/2019 |
| d7.1 | Design of exploitation plan | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.2 | OED CIA promotion | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.3 | Internship promotion | UNIGAL | Florin | Nedelcuț | 14/04/2019 |
| d7.4 | Promotion of startups | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.5 | Public-private collaboration | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.6 | Promotion and exploitation of the ICT platform | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.7 | Proposal for recognition of the courses degree | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d7.8 | Draft of a formal regulatory proposal | UNIGAL | Florin | Nedelcuț | 14/09/2019 |
| d.8.1 | Kickoff and Consortium meetings | UNISANN | Pasquale | Daponte | 14/05/2019 |
| d.8.2 | Coordination activities | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d.8.3 | Financial management reports | UNISANN | Pasquale | Daponte | 14/09/2019 |
| d.8.4 | Communication with EACEA agency | UNISANN | Pasquale | Daponte | 14/09/2019 |

# 5. Example of Template to provide deliverable information

| Deliverable Type |  |
| --- | --- |
| Result Number |  |
| Date of Delivery | XX.XX.XXXX |
| Author(s) | Xxxxxx Xxxxx (Partner Name) |
| Reviewer | Xxxxxx Xxxxx (Partner Name) |
| Review date | XX.XX.XXXX |
| Reviewer | Xxxxxx Xxxxx (Partner Name) |
| Review date | XX.XX.XXXX |

# 6. Example of Template to provide information about Deliverable Versioning and Contribution History

| Version | Date | Reason | Modified by |
| --- | --- | --- | --- |
| 01 | XX.XX.XXXX | xxxxx | Xxxxxx Xxxxxxxx |
| 02 | XX.XX.XXXX | xxxxx | Xxxxxx Xxxxxxxx |
| 03 | XX.XX.XXXX | xxxxx | Xxxxxx Xxxxxxxx |
| 04 | XX.XX.XXXX | xxxxx | Xxxxxx Xxxxxxxx |
| 05 | XX.XX.XXXX | xxxxx | Xxxxxx Xxxxxxxx |